## Backlog
id | theme | as a/an | I want to… | so that… | notes | acceptance criteria | added in sprint | story points
1 | content | User | be able to see a "Contact Us" button | I can contact the development team for suggestions or bugs |  |  | 1 | 20 | As a / an User I want to be able to see a "Contact Us" button so that I can contact the development team for suggestions or bugs
2 | content | User | see the logo and name of the development team | I would know what team I'm referring to |  |  | 1 | 20 | As a / an User I want to see the logo and name of the development team so that I would know what team I'm referring to
3 | content | User | see all the shapes in the canvas | I would know the look of the shapes |  |  | 1 | 130 | As a / an User I want to see all the shapes in the canvas so that I would know the look of the shapes
4 | content | User | see the shape IDs | I can identify what shape it is |  |  | 1 | 50 | As a / an User I want to see the shape IDs so that I can identify what shape it is
5 | content | User | read from a shape file | I can set the default dimensions of the shape |  |  | 1 | 50 | As a / an User I want to read from a shape file so that I can set the default dimensions of the shape
6 | content | User | keep track of all shapes currently being rendered | I can know what shapes are being drawn on the canvas |  |  | 2 | 20 | As a / an User I want to keep track of all shapes currently being rendered so that I can know what shapes are being drawn on the canvas
7 | content | User | add shapes | I can instatiate different types of shapes on the canvas |  |  | 2 | 50 | As a / an User I want to add shapes so that I can instatiate different types of shapes on the canvas
8 | content | User | remove shapes | I can remove the shapes that is not needed |  |  | 2 | 50 | As a / an User I want to remove shapes so that I can remove the shapes that is not needed
9 | content | User | make a shape listing report | I can see what shapes are on the canvas |  |  | 2 | 50 | As a / an User I want to make a shape listing report so that I can see what shapes are on the canvas
10 | content | User | sort shape listing report shapes by ID | I can easily see what shape it is |  |  | 2 | 50 | As a / an User I want to sort shape listing report shapes by ID so that I can easily see what shape it is

## Done
id | theme | as a/an | I want to… | so that… | notes | acceptance criteria | added in sprint | closed in sprint | story points
1 | content | User | be able to see a "Contact Us" button | I can contact the development team for suggestions or bugs |  |  | 1 | 1 | 20 | As a / an User I want to be able to see a "Contact Us" button so that I can contact the development team for suggestions or bugs
2 | content | User | see the logo and name of the development team | I would know what team I'm referring to |  |  | 1 | 1 | 20 | As a / an User I want to see the logo and name of the development team so that I would know what team I'm referring to
3 | content | User | see all the shapes in the canvas | I would know the look of the shapes |  |  | 1 | 1 | 130 | As a / an User I want to see all the shapes in the canvas so that I would know the look of the shapes
4 | content | User | see the shape IDs | I can identify what shape it is |  |  | 1 | 1 | 50 | As a / an User I want to see the shape IDs so that I can identify what shape it is
5 | content | User | read from a shape file | I can set the default dimensions of the shape |  |  | 1 | 1 | 50 | As a / an User I want to read from a shape file so that I can set the default dimensions of the shape
6 | content | User | keep track of all shapes currently being rendered | I can know what shapes are being drawn on the canvas |  |  | 2 | 2 | 20 | As a / an User I want to keep track of all shapes currently being rendered so that I can know what shapes are being drawn on the canvas
7 | content | User | add shapes | I can instatiate different types of shapes on the canvas |  |  | 2 | 2 | 50 | As a / an User I want to add shapes so that I can instatiate different types of shapes on the canvas
8 | content | User | remove shapes | I can remove the shapes that is not needed |  |  | 2 | 2 | 50 | As a / an User I want to remove shapes so that I can remove the shapes that is not needed
9 | content | User | make a shape listing report | I can see what shapes are on the canvas |  |  | 2 | 2 | 50 | As a / an User I want to make a shape listing report so that I can see what shapes are on the canvas
10 | content | User | sort shape listing report shapes by ID | I can easily see what shape it is |  |  | 2 | 2 | 50 | As a / an User I want to sort shape listing report shapes by ID so that I can easily see what shape it is

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
0 | 190 | 0 | 0 | 0% | 0 | 190
1 | 180 | 50 | 0 | 22% | 0 | 180
2 | 180 | 130 | 80 | 42% | -80 | 100
3 | 90 | 220 | 80 | 71% | -80 | 10
4
5
6
7
8
9
10

## Lists
0
5
10
20
30
50
80
130
200
400
1000