## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
As a user, the program should keep track of all shapes currently being rendered by the 2D modeler | Task 1 | Jon | Closed | 1 | 1 | 0.5 | 0.5 | 0 | 0
| Task 2 | Leo | Closed | 1 | 0.5 | 1 | 0.5 | 0 | 0
| Task 3 | Martin | Closed | 1 | 0 | 0 | 0 | 1 | 0
As a user, I should be able to add shapes. | Task 1 | Wilson | Closed | 3 | 2 | 0.5 | 1 | 1 | 1
| Task 2 | Alexi | Closed | 3 | 1 | 0.5 | 0.5 | 1 | 0
| Task 3 | Martin | Closed | 3 | 0 | 0 | 0.5 | 0.5 | 0
As a user, I should be able to remove shapes. | Task 1 | Alexi | Closed | 4 | 1 | 2 | 1 | 1 | 0
| Task 2 | Wilson | Closed | 4 | 0.5 | 1 | 0.5 | 2 | 0
As a user, the program should be able to make a shape listing report sorted by their ID's | Task 1 | Alexi | Closed | 2 | 1 | 0.5 | 1 | 0 | 0
| Task 2 | Jon | Closed | 2 | 1 | 0.5 | 1 | 1 | 1
| Task 3 | Martin | Closed | 2 | 0 | 0 | 1 | 1
As a user, the shape listing report should be sorted by their ID's | Task 1 | Alexi | Closed | 2 | 0.5 | 0.5 | 1 | 0 | 0
| Task 2 | Leo | Closed | 2 | 2 | 0.5 | 0.5 | 1 | 0
| Total |  |  | 24 | 10.5 | 7.5 | 9 | 9.5 | 2
Sprint Goal
The Sprint goal (2nd sprint) is to have the project completed by the end of the 2 weeks.